## Sheet1
Software Engineering Spotify/News app: User Stories
Identifier | User Stories | Size (Points) | Priority | Time Estimate (Days): | Travel Velocity
REQ-1 | As a user, I would like to press a button, and have a list of songs related to the days news appear | 6 |  | 3 | 2
REQ-2 | As a user, I would like to be able to filter the songs based on the news they are related do (e.g politics, music, technology) | 4 |  | 2
REQ-3 | As a user, I would like to be able to login and have an account | 10 |  | 5
REQ-4 | As a user, I would like to edit my account/customise | 3 |  | 1.5
REQ-5 | As a user, I would like the app to remember my details so I dont have to type them in everytime I load the app | 10 |  | 5
REQ-6 | As a user, I would link to my account to spotify | 5 |  | 2.5
REQ-7 | As a user, I would like to be able to access the application through the internet. | 10 |  | 5
REQ-8 | As a mobile user, I would like to be able to access a mobile version of the app | 10 |  | 5
REQ-9 | As a user, I would like to create a playlist of songs that I've recieved from the app | 4 |  | 2
REQ-10 | As a admin, I want to be able to query user searches | 10 |  | 5
REQ-11 | As a admin, I want to be able to manage accounts | 10 |  | 5
High Priority
Medium Priority
Low Priority