## Sheet1
SPRINT 1
Task | Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Build C# GUI | 1.5 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0
Build C# function to call news API | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Build C# Funtion for extracting key words | 4 | 0 | 0 | 2 | 1 | 0 | 0 | 0
Build C# function to call spotify API | 4 | 0 | 0 | 0 | 2 | 1 | 0 | 0
C# Login system | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Account customisation | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Save user details | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Link account to spotify | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Actual Effort | 25.5 | 24 | 22 | 20 | 17 | 16 | 16 | 16
Ideal Effort | 25.5 | 21.8571 | 18.2143 | 14.5714 | 10.9286 | 7.2857 | 3.6429 | 0
SPRINT 2
Task | Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Research Python alternatives to C# Libraries | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Remake the keyword extractor in python | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0
Make a function to call news api | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0
Make a function to call spotify api | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0
Research GUI dev in python | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Make a GUI in python | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Actual Effort | 12.5 | 9 | 6 | 4 | 4 | 2 | 0 | 0
Ideal Effort | 12.5 | 10.7143 | 8.9286 | 7.1429 | 5.3571 | 3.5714 | 1.7857 | 0
SPRINT 3
Task | Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Filter newsapi qeury based on location/category | 6 | bar: Day 1 to Day 6
Create function to enable user to authorise application | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0
Create function to create spotify playlist | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Get headlines to appear when 'display results' pressed | 3 | 0 | 0.5 | 0.5 | 1 | 1 | 0 | 0
| Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Actual Effort | 13 | 12 | 10.5 | 8 | 5 | 3 | 1 | 0
Ideal Effort | 13 | 11.1429 | 9.2857 | 7.4286 | 5.5714 | 3.7143 | 1.8571 | -2.2204e-15