## Sheet1
Programming Log
Date | Pair Programming | Objective | Sprint No. | Error's in code | Solution | Status
2019-10-23 | Ben (Driver) & Josh (Observer) | Build function for retrieving top headlines (C#) | Sprint 1 | JSON Parsing not working | Switch language to Python
2019-10-23 | Craig (Driver) & Rob (Observer) | Build GUI for the application (C#) | Sprint 1 | C# Programming less compatible with APIs which made the whole Program harder to develop. | Switch language to Python
2019-10-28 | Yifan (Driver) & Rob (Observer) | Build function for extracting keywords from string (C#) | Sprint 1 | Initial keyword extraction algorithm failed | Used NLTK (Natural Language Toolit)
2019-10-28 | Josh (Driver) & Yifan (Observer) | Spotify create playlist based on words (C#) | Sprint 1 | C# was less compatible with Spotify API | Switch to Python
2019-11-04 | Rob (Driver) & Craig (Observer) | Build GUI for the application (Python) | Sprint 2 | Adding/positioning elements such as buttons is more difficult than in C# Windows Forms. | Use suitable and easy to use library (tkinter)
2019-11-04 | Ben (Driver) & Josh (Observer) | Build function for retrieving top headlines (Python) | Sprint 2 | Converting C# to Python | Make changes to the code when pasting into Python
2019-11-08 | Yifan (Driver) & Josh (Observer) | Build function for extracting keywords from string (Python) | Sprint 2 | Converting C# to Python | Make changes to the code when pasting into Python
2019-11-08 | Josh (Driver) & Craig (Observer) | Spotify create playlist based on words (Python) | Sprint 2 | Converting C# to Python | Make changes to the code when pasting into Python
2019-11-11 | Josh (Driver) & Ben (Observer) | Put together the functions to work with GUI | Sprint 3 | N/A | N/A
2019-11-11 | Josh (Driver) & Ben (Observer) | Spotify create playlist based on keywords | Sprint 3 | Navigating JSON structure of the return values | Printing out JSON and reading it
2019-11-19 | Yifan (Driver) & Craig (Observer) | Display headlines used by playlist + Keywords | Sprint 3 | N/A | N/A