## Sheet1
2019-10-22
Product Backlog | Story Points (hours) | Priority(Client) | Priority(User) | Priority(Developer)
C# GUI with button to call a function | 0.5 | 10 | 10 | 3
C# function to call to News API to get top headlines | 2 | 0 | 0 | 10
C# function - keyword extractor, extracts keywords from a string (headline) | 4 | 5 | 0 | 9
C# function to call spotify API and produce a list of songs based on search strings (keywords from headlines) | 4 | 5 | 10 | 8
Login system for C# application | 5 | 7 | 8 | 3
Allow for editing/customising account page | 3 | 5 | 8 | 4
Save files for remembering details to prevent logging in everytime | 3 | 7 | 10 | 0
Look into linking accounts to spotify (generate personal playlists) | 3 | 6 | 10 | 3
2019-10-30
Product Backlog Groomed | Story Points (hours) | Priority(Client) | Priority(User) | Priority(Developer)
Python GUI with button to call a function | 0.5 | 10 | 10 | 3
Python function to call to News API to get top headlines | 2 | 0 | 0 | 10
Python function - keyword extractor, extracts keywords from a string (headline) | 4 | 5 | 0 | 9
Python function to call spotify API and produce a list of songs based on search strings (keywords from headlines) | 4 | 5 | 10 | 8
Login system for Python application | 5 | 7 | 8 | 3
Allow for editing/customising account page | 3 | 5 | 8 | 4
Save files for remembering details to prevent logging in everytime | 3 | 7 | 10 | 0
Look into linking accounts to spotify (generate personal playlists) | 3 | 6 | 10 | 10
2019-11-07
Product Backlog Groomed | Story Points (hours) | Priority(Client) | Priority(User) | Priority(Developer)
Python GUI with button to call a function | 0.5 | 10 | 10 | 3
Python function to call to News API to get top headlines | 2 | 0 | 0 | 10
Python function - keyword extractor, extracts keywords from a string (headline) | 4 | 5 | 0 | 9
Python function to call spotify API and produce a list of songs based on search strings (keywords from headlines) | 4 | 5 | 10 | 8
Login system for Python application | 5 | 7 | 8 | 3
Allow for editing/customising account page | 3 | 5 | 8 | 4
Save files for remembering details to prevent logging in everytime | 3 | 7 | 10 | 0
Look into linking accounts to spotify (generate personal playlists) | 3 | 6 | 10 | 10
Filter songs based on news type | 4 | 10 | 6 | 9
Filter songs based on location | 1 | 10 | 7 | 9
All headlines songs need to be generated in 1 unique playlist | 2 | 10 | 10 | 10
Display headline results | 1 | 7 | 3 | 7